## Checklist
ML23-06 Magic Wand with an Arduino Nano 33 BLE sense
Name, Vorname | Walse Adhiraj |  |  | cc:Hochschule Emden Leer Universit of Applied Sciences
Matr.-Nr | 7025711 |  |  | MBIDA
Prof. Elmar Wings
Checklist
update every day!
No. | Topic | done | date
First two weeks
1 | read ProjectManagement/BestPractice.pdf | 1st Week | 2024-10-02
2 | fulfill author.xlsx |  | 2024-10-02
3 | Install TeXLive |  | 2024-10-02
4 | install TeXStudio |  | 2024-10-02
5 | install Sumatrapdf |  | 2024-10-02
6 | configure TeXStudio |  | 2024-10-02
7 | test template report |  | 2024-10-02
8 | test template poster |  | 2024-10-02
9 | test template Presentations/template |  | 2024-10-02
10 | install doxygen |  | 2024-10-02
11 | readme.md |  | 2024-10-02
12 | literature research | 2nd week | 2024-10-10
13 | bib file |  | 2024-10-10
14 | bibliography |  | 2024-10-10
15 | pdf files |  | 2024-10-10
16 | presentation "Literature" |  | 2024-10-10
17 | challenges with citations |  | 2024-10-10
18 | write n introduction with citations |  | 2024-10-10
19 | presentation "Introduction" |  | 2024-10-10
20 | project plan | 3rd week | 2024-10-15
21 | fulfill the list "Resulting Objects" |  | 2024-10-15
22 | presentation "Project Plan" |  | 2024-10-15
23 | Readme.md |  | 2024-10-15
Processing the project
24 | update project plan | 4th week | 2024-10-25
25 | update the list "Resulting Objects" |  | 2024-10-25
26 | presentation "Project Plan" II |  | 2024-10-25
27 | rename all tex files along the project plan |  | 2024-10-25
28 | delete or add additional TeX or Python projects, e.g. Manual |  | 2024-10-25
29 | List of Material |  | 2024-10-25
30 | Manual |  | 2024-10-25
31 | domain knowledge | 5th week | 2024-11-05
32 | algorithm |  | 2024-11-25
33 | tools |  | 2024-11-15
34 | methodology |  | 2024-12-05
35 | database | 6th week | 2024-12-06
36 | database description |  | 2024-12-12
37 | database discussion |  | 2024-12-12
38 | Homework "Literature" | 7th week | 2024-12-13
39 | Homework "John Ousterhout"
40 | updated README.md |  | 2024-12-15
41 | updated Project plan | 8th weeek | 2024-12-20
42 | updated Resulting objects |  | 2024-12-30
43 | Evaluation |  | 2024-12-31
44 | Validation |  | 2025-01-01
45 | Homework "UpdatedLiterature" | 9th week
46 | Development structure
47 | Development Environment
48 | From Development to Deployment | 10 th weeek
49 | Flow Chart
50 | tests
Final stage
51 | check: all website as pdf-file? | done | 2025-01-31
52 | check: all pdfs in the folder Documents? | done | 2025-01-31
53 | check: all images okay? | done | 2025-01-31
54 | check spelling | done | 2025-01-31
55 | ready minimal one day before deadline | done | 2025-01-31
56 | check: no undesired latex comments such as \newline, \pagebreak, \newpage... | done | 2025-01-31
57 | check: proper naming for png | done | 2025-01-31
58 | check: no usage of `_` for naming | done | 2025-01-31
59 | check: all citations are in line with the best practices | done | 2025-01-31
60 | check: there exist README.md and author.xlsx | done | 2025-01-31
61 | check: the main source of literature and its relevance | done | 2025-01-31
62 | check: the bib file contains all required informations | done | 2025-01-31
63 | check: the project plan is precise and understandable | done | 2025-01-31
64 | check: the number of virtuals (tables, figures, images,…) are enough | done | 2025-01-31
65 | check: there is no table attached as png | done | 2025-01-31
66 | check: there is no code attached as png | done | 2025-01-31
67 | check: images and tables are mentioned in the main text | done | 2025-01-31
68 | check: usage of tikz | done | 2025-01-31
69 | check: keywords are precise | done | 2025-01-31

## Projekt Plan V1.0 (deut.)
Das Liebesleben der Maikäfer bei Nacht
|  | KW | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | ... | 26 | 27 | ... | 30
|  | lfd. Woche | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | ... | 16 | 17 | ... | 20
TP-Nr. | TP-Name | Dauer
1 | Einarbeitung / Literatur | 2.5
2 | ... | 1
3 | ... | ...
4 |  | 2
5 |  | ...
6
7
8
9
10
11
12
13
14 | Verfassen PA / BT / DA / MT | ...
15 | Durchsicht | 2
16 |  | 1.5
17 | Kolloquium | 1
| Urlaub / Feiertage | [5 empty] | Geburt |  |  | Ostern |  | Pfingsten
| Anmeldung / Abgabe | [7 empty] | 34. März |  |  |  |  | 34. Juli
Besprechungen
PJ = Projekt
| TP = Teilprojekt | [8 empty] | x = f(Studiengang)
Anmeldung
Abgabe
Hermann Meyer
Matr.-Nr. 1112569
7. Sem PVT
Version: 1.3 / 29.02.2025
Persönliche Daten
Vorläufiger Titel
der Arbeit
Nr. des Teilprojektes
(10 - 20 incl. Kolloquium)
Bezeichnung des Teilprojektes
Kalenderwoche des Jahres = zeitl. Lage
Laufende Woche der Arbeit seit Start => Dauer
planbare Ausfallzeiten
(selbst, Partner, Prüfer)
Anmeldetermin = gepl. Abgabetermin
abzgl. x Monate (für BT/DA/MT)
geplanter Abgabetermin
Teilprojekt
Balkenlänge = geschätzte Dauer; kleinste Einheit = 0,5 Wochen
subjektiver Abarbeitungzustand des TP bei korrelierender Besprechung
gepl. Besprechungstermin mit Erstprüfer
Planungsstand des Projektplans (Version, Datum)
spontan + intuitiv geschätzte Dauer des TP;
kleinste Einheit = 0,5 Wochen
Projektplan-Muster für eine Projektarbeit (PA) / Bachelor Thesis (BT) / Diplomarbeit (DA) / Master Thesis (MT)
cc: - Firmen-Betreuer
- PJ-Partner
- Erstprüfer
Empfänger
des PJ-Plans
Plan hier: Bearbeitung wegen Auszeit unterbrechen
Plan hier: Bearbeitung trotz Feiertage fortführen
1
2
2
3
5
4
6
7
8
9
10v
11v

## Project Plan V1.0 (eng.)
The Love Life of Cockchafers at Night
|  | Week of Year | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | ... | 35 | 36 | ... | 39
|  | Project Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | ... | 26 | 27 | ... | 30
SP No. | SP's Title | Duration
1 | Informative activities / literature | 2.5
2 | ... | 1
3 | ... | ...
4 |  | 2
5 |  | ...
6
7
8
9
10
11
12
13
14 | Writing of thesis | ...
15 | First checking through by examiner | 2
16 | Optimization | 1.5
17 | Colloquium | 1
| Vacation / holidays | [5 empty] | Birth |  |  | Easter |  | Pentecost
| Enrolement / Submission | [7 empty] | March 34 |  |  |  |  | July 34
Meetings
SP = Sub-project
x = f(course of study)
Enrolement
Submission
Hermann Meyer
Matr.-Nr. 1112569
7. Sem PVT
Version: 1.0 / 29.02.2025
Personal Data
Preliminary title
of thesis
SP's number
(10 - 20 SPs incl. Colloquium)
SP's title
Week of year
Weeks since start of project => duration
schedulable time outs
(causes: yourself, partners, examiner, ..)
Date of enrolement = scheduled date of submission minus x months
scheduled date of submission
SP
Length of bar = estimated duration; smallest unit = 0.5 week
Actual state of SP's completion at time of corresponding meeting
(subjective estimation)
Scheduled meeting with first examiner
Project plan of (version / date)
Duration of SP estimated in the beginning
(spontaneously and intuitivly)
smallest unit = 0,5 week
Template for Project Plan of Master's Thesis
cc: - Contact person in company
- Project partner
- First examiner
Receivers of this project plan
Scheduled interruption of work
Scheduled to continue work despite of holiday
Colloquium
1
2
2
3
5
4
6
7
8
9
10v
11v

## Project Plan
cc:Hochschule Emden Leer Universit of Applied Sciences
MBIDA
|  |  |  | ML23-06 Magic Wand with an Arduino Nano 33 BLE sense | [14 empty] | Prof. Elmar Wings
|  | Week of Year | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7
|  | Project Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
SP No. | SP's Title | Duration
1 | Software Installation (GitHub, TexLive, TexStudio, Sumatrapdf, doxygen) | 2
2 | Clone Repository | 1
3 | Author and Checklist Update | 2
4 | Project Plan Creation | 2
5 | Informative activities / literature | 16
6 | Prepare Report Structure | 3
7 | Introduction Writing | 5
8 | Problem Description | 5
9 | Hardware Description Section | 5
10 | Software Description | 5
11 | Bill Of Materials Required | 5
12 | Data Mining Algorithm Writing | 7
13 | Manual Preparation | 5
14 | Data selection Writing | 6
15 | Data preprocessing Writing | 6
16 | Data transformation Writing | 6
17 | Data Mining Writing | 7
18 | Interpretation Writing | 7
19 | Validation Writing | 7
20 | Given Documentation and Improvements Preparation | 5
21 | Expect Deployment Writing | 5
22 | KDD research for project | 6
23 | Testing Basic HW Features | 3
24 | Implementation of Data KDD Model | 10
25 | Develop Initial Code for ML Model | 5
26 | Testing on the HW | 6
27 | Optimize the Model - Python | 5
28 | Convert ML Model to C++ | 5
29 | Testing the model behavior with HW | 6
30 | Improving Model with real cases | 8
31 | Result / Conclusion / Next Steps | 4
32 | Poster Preparation | 4
33 | Presentation Preparation | 4
34 | Final Modification | 12
| Vacation / holidays |  | ML23-06 Magic Wand with an Arduino Nano 33 BLE sense 52 13: X-Mas; Prof. Elmar Wings 7 20: 27th January Hardware return
| Enrolement / Submission |  | ML23-06 Magic Wand with an Arduino Nano 33 BLE sense 3 16: 16th January Final Presentation; Prof. Elmar Wings 7 20: 31th January Project Deadline
Meetings
Template for Project Plan of Project-T
Srikanth Nanda
Matr.-Nr. 7026002
1. Sem MBIDA
Sudeshna Nanda
Matr.-Nr. 7026003
1. Sem MBIDA
Adhiraj Walse
Matr.-Nr. 7025193
2. Sem MBIDA
All Groupmates

## Resulting objects
"ML23-06 Magic Wand with an Arduino Nano 33 BLE sense"
Name, Vorname | Walse Adhiraj |  |  | cc: Hochschule Emden Leer Universit of Applied Sciences
Matr.-Nr | 7025711 |  |  | MBIDA
Prof. Elmar Wings
List of all Resulting Objects
Subtask | Resulting objects | done | date
Literature | List of keywords |  | 2024-10-10
| Brief description of the sources |  | 2024-10-11
| bib file |  | 2024-10-12
| Bibliography in the report |  | 2024-10-12
| pdf documents |  | 2024-10-12
| quality check |  | 2024-10-12
Manual |  | done
Material List and Hardware, software requirements |  | done
| Software Installation (GitHub, TexLive, TexStudio, Sumatrapdf, doxygen) | Done in the final report | 2024-10-02
| Clone Repository | Done in the final report | 2024-10-02
| Author and Checklist Update | Done in the final report | 2024-10-02
| Project Plan Creation | Done in the final report | 2024-10-15
| Informative activities / literature | Done in the final report | 2024-10-20
| Prepare Report Structure | Done in the final report | 2024-10-20
| Introduction Writing | Done in the final report | 2024-10-20
| Problem Description | Done in the final report | 2024-10-20
| Hardware Description Section | Done in the final report | 2024-10-25
| Software Description | Done in the final report | 2024-10-25
| Bill Of Materials Required | Done in the final report | 2024-10-25
| Data Mining Algorithm Writing | Done in the final report | 2024-10-25
| Manual Preparation | Done in the final report | 2024-10-21
| Data selection Writing | Done in the final report | 2024-11-02
| Data preprocessing Writing | Done in the final report | 2024-11-02
| Data transformation Writing | Done in the final report | 2024-11-02
| Data Mining Writing | Done in the final report | 2024-11-10
| Interpretation Writing | Done in the final report | 2024-11-10
| Validation Writing | Done in the final report | 2024-11-12
| Given Documentation and Improvements Preparation | Done in the final report | 2024-11-12
| Expect Deployment Writing | Done in the final report | 2024-11-20
| KDD research for project | Done in the final report | 2024-11-20
| Testing Basic HW Features | Done in the final report | 2024-11-20
| Implementation of Data KDD Model | Done in the final report | 2024-12-01
| Develop Initial Code for ML Model | Done in the final report | 2024-12-01
| Testing on the HW | Done in the final report | 2024-12-15
| Optimize the Model - Python | Done in the final report | 2024-12-15
| Convert ML Model to C++ | Done in the final report | 2024-12-20
| Testing the model behavior with HW | Done in the final report | 2024-12-20
| Improving Model with real cases | Done in the final report | 2024-12-20
| Result / Conclusion / Next Steps | Done in the final report | 2025-01-10
| Poster Preparation | Done in the final report | 2025-01-15
| Presentation Preparation | Done in the final report | 2025-01-16
| Final Modification | Done in the final report | 2025-01-31
Projectplan-Project (10credits) in Master Course "Business Intelligence and Data Analytics"